## Sheet1
Task ID | Task | Assigned to | Assigned | Completion | Status | Task ID | Task | Assigned to | Assigned | Completion | Status
1 | Introduction(doc) | 008 Richa | 2022-02-21 | 2022-03-15 | completed | 1 | Timeline | 055 Janvi | 2022-02-18 | 2022-02-21 | completed | work | status
2 | USE CASE DIAGRAM |  | 2022-02-21 | 2022-02-28 | completed | 2 | Assumptions, Process model(doc) |  | 2022-02-21 | 2022-03-15 | completed
3 | (Verification) Login, Signup |  | 2022-03-12 |  | in progress | 3 | (Verification) Login, Signup |  | 2022-03-12 |  | in progress
4 | [5 empty] | 4 | ACTIVITY DIAGRAM |  | 2022-03-28 |  | yet to start
5 | [5 empty] | 5 | SEQUENCE DIAGRAM |  | 2022-03-28 |  | yet to start
Task ID | Task | Assigned to | Assigned | Completion | Status | Task ID | Task | Assigned to | Assigned | Completion | Status
1 | Problem Statement, FR(doc) | 032 Peril | 2022-02-21 | 2022-03-15 | completed | 1 | Objectives(doc) | 064 Piyush | 2022-02-21 | 2022-03-15 | completed
2 | USE CASE DIAGRAM |  | 2022-02-21 | 2022-02-28 | completed | 2 | (CRUD)Manage Product |  | 2022-03-12 |  | in progress
3 | Wallet, Place Bid |  | 2022-03-12 |  | in progress | 3 | CLASS DIAGRAM |  | 2022-03-28 |  | yet to start
4 | [5 empty] | 4
5 | [5 empty] | 5
Task ID | Task | Assigned to | Assigned | Completion | Status | Task ID | ` | Assigned to | Assigned | Completion | Status
1 | Specific Requirement(doc) | 039 Urja | 2022-02-21 | 2022-03-15 | completed | 1 | NFR(doc) | 106 Jenish | 2022-02-21 | 2022-03-15 | completed
2 | (Verification) Login, Signup |  | 2022-03-12 |  | in progress | 2 | Wallet, Place Bid |  | 2022-03-12 |  | in progress
3 | ACTIVITY DIAGRAM |  | 2022-03-28 |  | yet to start | 3 | ACTIVITY DIAGRAM |  | 2022-03-28 |  | yet to start
4 | SEQUENCE DIAGRAM |  | 2022-03-28 |  | yet to start | 4 | SEQUENCE DIAGRAM |  | 2022-03-28 |  | yet to start
5 | [5 empty] | 5
Task ID | Task | Assigned to | Assigned | Completion | Status | Task ID | Task | Assigned to | Assigned | Completion | Status
1 | Existing System, users(doc) | 043 Mishel | 2022-02-21 | 2022-03-15 | completed | 1 | Project Scope(doc) | 128 Shail | 2022-02-21 | 2022-03-15 | completed
2 | USE CASE DIAGRAM |  | 2022-02-21 | 2022-02-28 | completed | 2 | (CRUD)Manage Product |  | 2022-03-12 |  | in progress
3 | (CRUD)Manage Product |  | 2022-03-12 |  | in progress | 3 | CLASS DIAGRAM |  | 2022-03-28 |  | yet to start
4 | [5 empty] | 4
5 | [5 empty] | 5
Task ID | Task | Assigned to | Assigned | Completion | Status
1 | Constraints(doc) | 048 Jenish | 2022-02-21 | 2022-03-15 | completed
2 | Wallet, Place Bid |  | 2022-03-12 |  | in progress
3 | CLASS DIAGRAM |  | 2022-03-28 |  | yet to start
4
5